## Jira
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers | Watchers Id | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Inward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Outward issue link (Blocks) | Inward issue link (Relates) | Inward issue link (Relates) | Outward issue link (Relates) | Attachment | Attachment | Custom field (Actual end) | Custom field (Actual start) | Custom field (Assessment due date) | Custom field (Atlas project key) | Custom field (Atlas project status) | Custom field (Author) | Custom field (Author)Id | Custom field (Business Analyst) | Custom field (Business Analyst)Id | Custom field (Category) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Compass) | Custom field (Dependencies) | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Flagged) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Phase) | Custom field (Rank) | Custom field (Request Type) | Sprint | Sprint | Sprint | Sprint | Custom field (Start date) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Testing estimate) | Custom field (Total forms) | Custom field ([CHART] Date of First Response) | Comment | Comment | Parent | Parent summary | Status Category
Linting | PRO-104 | 10103 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-19 20:41 | 2023-10-19 20:41 | 2023-10-19 21:55 |  |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P4 | 0¦i000gn: | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | To Do
Documentation | PRO-103 | 10102 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-19 20:36 | 2023-10-19 20:37 | 2023-10-19 20:36 |  |  | 0 | Document the codebase |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P4 | 0¦i0003r:n |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | To Do
create databases | PRO-102 | 10101 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-11 14:33 | 2023-10-15 21:31 | 2023-10-15 21:31 | 2023-10-15 12:02 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P4 | 0¦i0003x:j |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
Backend ¦ final database changes (we can only hope) | PRO-101 | 10100 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-04 20:55 | 2023-10-15 21:31 | 2023-10-08 16:23 | 2023-10-08 16:23 |  | 0 | modify the existing databases to match all the data Sean is going to add into the database in [https://deco3801.atlassian.net/browse/PRO-100¦https://deco3801.atlassian.net/browse/PRO-100¦smart-link]. Let’s hope these changes are final |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P4 | 0¦i0003r:0i |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 2 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
Data population | PRO-100 | 10099 | Task | In Progress | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 22:54 | 2023-10-11 15:14 | 2023-10-14 11:49 |  |  | 0 | Populate the data according to the excel sheet attached to this jira. [^PRO-100_Politician_data_populate.xlsx] |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 01/Oct/23 10:54 PM;6393c7579960988ef6c31a45;PRO-100_Politician_data_populate.xlsx;https://deco3801.atlassian.net/rest/api/3/attachment/content/10036 | [26 empty] | 0¦i0003x:i |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 10 |  |  |  |  | 2 |  |  |  |  | 10003 | Admin | In Progress
UI implementation ¦ campaign details | PRO-99 | 10098 | Task | Code review/test | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 22:13 | 2023-10-18 21:11 | 2023-10-04 16:00 |  |  | 0 | *Success criteria:* develop the political campaign details according to the image attached below. The implementation of this page will be dependent on the endpoint routes created in [https://deco3801.atlassian.net/browse/PRO-95¦https://deco3801.atlassian.net/browse/PRO-95¦smart-link]. Please Liaison with this developer to make sure you are equipped with the necessary data to complete this task. !image-20231001-121331.png¦width=1193,height=909! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 01/Oct/23 10:13 PM;6393c7579960988ef6c31a45;image-20231001-121331.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10035 | [26 empty] | 0¦i0003r:h |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 10 |  |  |  |  | 5 |  |  |  |  | 10002 | Frontend | In Progress
UI implementation ¦ filter search | PRO-98 | 10097 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 22:10 | 2023-10-04 16:00 | 2023-10-04 16:01 |  |  | 0 | *Success criteria:* Develop filters for the country (Australia only) Political Party and Position of each political candidate. NOTE: despite the image, a dropdown will be necessary to implement these filters. This should be achievable in Javascript (i.e. frontend) only, but liaison with developer of [https://deco3801.atlassian.net/browse/PRO-95¦https://deco3801.atlassian.net/browse/PRO-95¦smart-link] to ensure you have enough data to drive these Filters. !image-20231001-120817.png¦width=878,height=446! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 01/Oct/23 10:10 PM;6393c7579960988ef6c31a45;image-20231001-120817.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10034 | [20 empty] | Impediment | [5 empty] | 0¦i000gf: | [6 empty] | 5 |  |  |  |  | 1 |  |  | 04/Oct/23 4:00 PM;6393c7579960988ef6c31a45;(flag) Flag added Delete |  | 10002 | Frontend | To Do
UI implementation ¦ Political figure cards | PRO-97 | 10096 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 22:03 | 2023-10-04 15:59 | 2023-10-04 15:59 |  |  | 0 | *Requirements:* Develop a component library to create cards as per specification of the image below !image-20231001-120343.png¦width=642,height=497! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-95 | [18 empty] | 01/Oct/23 10:03 PM;6393c7579960988ef6c31a45;image-20231001-120343.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10033 | [20 empty] | Impediment | [5 empty] | 0¦i000g7: | [6 empty] | 10 |  |  |  |  | 2 |  |  | 04/Oct/23 3:59 PM;6393c7579960988ef6c31a45;(flag) Flag added delete |  | 10002 | Frontend | To Do
Bug fixes ¦ sessionManager | PRO-96 | 10095 | Task | In Progress | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 22:02 | 2023-10-08 12:00 | 2023-10-06 14:44 |  |  | 0 | I observed some bugs when trying to set recent articles, utilising the articleManager _getitem_ method. If an article is already persisted to the database, on initialisation, the article is not moved to cache. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i0003x:m |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 3 |  |  |  |  | 2 |  |  |  |  | 10054 | designing | In Progress
Backend ¦ Infrastructure for politician cards | PRO-95 | 10094 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 21:59 | 2023-10-04 15:57 | 2023-10-04 15:57 |  |  | 0 | *Requirements* Develop DOM models and carefully consider the table structures needed to implement the politician ‘cards’ in the image below. Some fields will need to be added to existing Politician table since it’s original creation. This Jira will also require sessionmanager updates, in addition to any API endpoint routes which are necessary to make this structure work. *Suggestions:* Add Political party, Political position and ‘about’ and campaign ID to the politician table Create Politician_CampaignInfo table for all campaign related info Create Campaign name table !image-20231001-115352.png¦width=786,height=851! !image-20231001-115723.png¦width=820,height=634! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-97 | [13 empty] | 01/Oct/23 9:59 PM;6393c7579960988ef6c31a45;image-20231001-115352.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10032 | 01/Oct/23 9:59 PM;6393c7579960988ef6c31a45;image-20231001-115723.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10031 | [19 empty] | Impediment |  |  |  |  | P4 | 0¦i000fr: | [6 empty] | 10 |  |  |  |  | 1 |  |  | 04/Oct/23 3:57 PM;6393c7579960988ef6c31a45;(flag) Flag added delete |  | 10008 | Backend | To Do
Backend ¦ unwind the summary field from article table | PRO-94 | 10093 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-10-01 10:45 | 2023-10-02 10:02 | 2023-10-19 22:03 | 2023-10-02 10:02 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P4 | 0¦i0003s:k9 |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | Done
persist bias keywords | PRO-93 | 10092 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-25 19:22 | 2023-10-02 10:02 | 2023-09-25 19:29 | 2023-10-02 10:02 |  | 0 | persist the bias keywords to a database so that [~accountid:70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a] can persist this in the articleManager. To be reviewed by [~accountid:70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a] in code review |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | [15 empty] | P4 | 0¦i0003s:kr |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 3 |  |  |  |  | 1 | [6 empty] | Done
New table for article bias keywords | PRO-91 | 10090 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-24 17:10 | 2023-10-01 15:40 | 2023-10-01 15:39 | 2023-10-01 15:40 |  | 0 | New table updates Update [~accountid:70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a] once in code review |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | [16 empty] | 0¦i0003s:r |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 5 |  |  |  |  | 4 |  |  | 01/Oct/23 3:40 PM;6393c7579960988ef6c31a45;[https://deco3801.atlassian.net/browse/PRO-93¦https://deco3801.atlassian.net/browse/PRO-93¦smart-link].sql file |  | 10008 | Backend | Done
UI Implementation ¦ Political figure webpage | PRO-90 | 10089 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-24 16:33 | 2023-10-01 15:57 | 2023-10-01 23:00 | 2023-10-01 15:57 |  | 0 | Implement all the endpoints needed to create this: !image-20230924-063250.png¦width=590,height=675! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 | [18 empty] | 24/Sep/23 4:33 PM;6393c7579960988ef6c31a45;image-20230924-063250.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10030 | [25 empty] | P3 | 0¦i0003s:m |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 10 |  |  |  |  | 2 |  |  |  |  | 10002 | Frontend | Done
new fields to article table | PRO-89 | 10088 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-23 10:38 | 2023-09-24 17:02 | 2023-10-19 22:03 | 2023-09-24 17:02 |  | 0 | Add the following new fields to the ``article`` table: ArticleHeader VARCHAR1000 ArticleText TEXT ArticleSummaryParagraph TEXT |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i0003v:i |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 1 |  |  |  |  | 0 | [6 empty] | Done
Backend refactoring, documentation check | PRO-88 | 10087 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-21 21:41 | 2023-09-24 17:02 | 2023-10-19 22:03 | 2023-09-24 17:02 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i0003v:9 |  | DECO3801 Sprint 3 ¦ P4 | [9 empty] | 1 | [6 empty] | Done
Backend ¦ more API routes | PRO-87 | 10086 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:52 | 2023-09-24 17:12 | 2023-10-11 16:17 |  |  | 0 | *Success Criteria:* * Create all the backend routes to be able to persist to this screen *Suggestions* * updates to retrieve politician data in sessionmanager, create helper functions if necessary * create API routes to handle requests |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 | [39 empty] | Impediment |  |  |  |  | P4 | 0¦i000fj: | [6 empty] | 4 |  |  |  |  | 3 |  |  | 24/Sep/23 5:12 PM;6393c7579960988ef6c31a45;(flag) Flag added delete - unknown |  | 10008 | Backend | To Do
Backend ¦ recents and most popular, politicians | PRO-86 | 10085 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:41 | 2023-10-04 20:41 | 2023-10-18 09:29 | 2023-10-04 20:41 |  | 0 | *Success Criteria:* Develop the ‘recents’ and most popular as per the wireframe design for the politician pages IMAGE FOR CONTEXT ONLY !image-20230920-104033.png¦width=785,height=580! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 | [15 empty] | PRO-78 | PRO-77 |  | 20/Sep/23 8:41 PM;6393c7579960988ef6c31a45;image-20230920-104033.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10028 | [25 empty] | P4 | 0¦i0003r:9 |  | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  |  |  | 10 |  |  |  |  | 2 |  |  |  |  | 10008 | Backend | Done
UI Implementation ¦ commenting | PRO-85 | 10084 | Task | Code review/test | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:38 | 2023-10-18 18:11 | 2023-10-06 14:21 |  |  | 0 | *Success Criteria:* Develop the commenting feature as per the wireframe design listed in the jira |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-84 | [18 empty] | 20/Sep/23 8:38 PM;6393c7579960988ef6c31a45;image-20230920-103759.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10027 | [25 empty] | P4 | 0¦i0003r:m |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 3 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | In Progress
Backend ¦ commenting | PRO-84 | 10083 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:31 | 2023-10-04 20:41 | 2023-10-17 22:42 | 2023-10-04 20:41 |  | 0 | *Success Criteria:* Update our application to handle a commenting system *Suggestions:* * Create a new database table (called _commenting_) to be able to save the comments. It should include a foreign reference to the article table (1-M relationship) * Create new class in _treansactiondataClient.py_ * create helper functions in new script (name it _dataClientHelper.py_) to add votes in polling * Create helper functions to retrieve the comments for a website * Update the session manager to manage the comments * Create routing request as per PRO-72 IMAGE FOR CONTEXT ONLY |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-85 | [40 empty] | 0¦i0003r:4 |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 10 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
UI implementation ¦ polling | PRO-83 | 10082 | Task | Code review/test | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:19 | 2023-10-14 10:52 | 2023-10-04 15:54 |  |  | 0 | *Success Criteria:* Develop the polling UI according to the specification of the wireframe. Requires implementation from PRO-82 !image-20230920-101922.png¦width=694,height=265! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-82 | [18 empty] | 20/Sep/23 8:19 PM;6393c7579960988ef6c31a45;image-20230920-101922.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10026 | [25 empty] | P4 | 0¦i0003r:p |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 3 |  |  |  |  | 2 |  |  |  |  | 10002 | Frontend | In Progress
Backend ¦ polling | PRO-82 | 10081 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 20:14 | 2023-10-04 20:41 | 2023-10-18 15:55 | 2023-10-04 20:41 |  | 0 | *Success Criteria:* Build all the backend implementation, including a API route to be able to handle polling requests *Suggestions:* * Create a GPT prompt to be able to create a poll (make updates to prompts.py) * Create a new database table (called _polling_) to be able to save the questions and votes from each. It should include a foreign reference to the article table (1-1 relationship) * Create new class in _treansactiondataClient.py_ * create helper functions in new script (name it _dataClientHelper.py_) to add votes in polling * Create helper functions to retrieve the votes for a particular poll * Update the session manager to manage the poll * Create routing request as per PRO-72 IMAGE FOR CONTEXT ONLY !image-20230920-101412.png¦width=631,height=254! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-83 | [13 empty] | 20/Sep/23 8:14 PM;6393c7579960988ef6c31a45;image-20230920-101412.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10025 | [25 empty] | P4 | 0¦i0003r:2 |  | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  |  |  | 10 |  |  |  |  | 3 |  |  |  |  | 10008 | Backend | Done
Backend ¦ toggle paragraph and bullet point form | PRO-81 | 10080 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 19:56 | 2023-09-24 17:01 | 2023-09-24 17:01 |  |  | 0 | *Context:* * We want to be able to provide the user with the ability to toggle in between bullet point and paragraph form *Success Criteria:* Develop a API Route than when requested, will send a response of the article in paragraph form. *Suggestions* * New Field in the article table (build a sql file for this) * update table structure article in transactiondataclient.py * potentially update session manager * Develop a new prompt to handle paragraph form * update prompt.py to handle paragraph prompt * create API route IMAGE FOR CONTEXT !image-20230920-095627.png¦width=878,height=467! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 | [18 empty] | 20/Sep/23 7:56 PM;6393c7579960988ef6c31a45;image-20230920-095627.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10024 | [20 empty] | Impediment |  |  |  |  | P4 | 0¦i000e7: | [6 empty] | 10 |  |  |  |  | 3 |  |  | 24/Sep/23 5:01 PM;6393c7579960988ef6c31a45;Flag to delete | 24/Sep/23 5:01 PM;6393c7579960988ef6c31a45;(flag) Flag added delete | 10008 | Backend | To Do
Backend ¦ persons of interest routes | PRO-80 | 10079 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 19:49 | 2023-10-01 09:15 | 2023-09-24 20:33 | 2023-10-01 09:15 |  | 0 | *Success Criteria:* Hook up the persons of interest ML model that Ron has created to the article, to search for any key names to display in header. *Suggestions:* * Create a specialised query to retrieve all politician names * run the ML model to retrieve all names from the article * Run a comparison and output in API route IMAGE FOR CONTEXT ONLY !image-20230920-094913.png¦width=584,height=117! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-56 | [13 empty] | 20/Sep/23 7:49 PM;6393c7579960988ef6c31a45;image-20230920-094913.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10023 | [26 empty] | 0¦i0003t: |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 5 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
UI ¦ recents table and most popular | PRO-79 | 10078 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 19:45 | 2023-10-15 17:18 | 2023-10-15 17:18 | 2023-10-15 17:18 |  | 0 | *Success Criteria:* Implement the recents and most viewed tabs as per the wireframe design !image-20230920-094509.png¦width=786,height=568! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-78 | PRO-77 | [17 empty] | 20/Sep/23 7:45 PM;6393c7579960988ef6c31a45;image-20230920-094509.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10022 | [26 empty] | 0¦i0003r:f |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 2 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | Done
Backend ¦ most popular | PRO-78 | 10077 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 19:41 | 2023-10-08 13:15 | 2023-10-06 14:44 | 2023-10-08 13:15 |  | 0 | *Success Criteria:* Implement the most popular news articles, to retrieve the top 10? recent articles *Suggestions:* * add article table field handle ‘viewing’ * create specialised query to retrieve top articles * NOT ESSENTIAL: create index on new viewing article * Create a specialised DDL to handle updates to new field * create routing response WIREFRAME IS FOR CONTEXT ONLY !image-20230920-094111.png¦width=806,height=601! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-79 | [12 empty] | PRO-86 | 20/Sep/23 7:41 PM;6393c7579960988ef6c31a45;image-20230920-094111.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10021 | [25 empty] | P4 | 0¦i0003r:1 |  | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  |  |  | 5 |  |  |  |  | 2 |  |  |  |  | 10008 | Backend | Done
Backend ¦ recents tab | PRO-77 | 10076 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 19:28 | 2023-10-02 10:02 | 2023-09-24 16:34 | 2023-10-02 10:02 |  | 0 | *Success Criteria:* * Build the route request that will retrieve recent articles from the user *Suggestions:* * Use the cached articles from the article Manager. Use this to generate a API response |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-79 | [12 empty] | PRO-86 | [27 empty] | 0¦i0003s:ki |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
UI implementation ¦ copy to clipboard | PRO-76 | 10075 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 18:59 | 2023-10-11 15:15 | 2023-10-04 15:54 | 2023-10-11 15:15 |  | 0 | *Success Criteria:* Create a copy to clipboard feature and implement the button. This should be attempted with [https://deco3801.atlassian.net/browse/PRO-74¦https://deco3801.atlassian.net/browse/PRO-74¦smart-link] |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [25 empty] | PRO-74 | [29 empty] | 0¦i0003r:09 |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | Done
UI updates ¦ Saved pages, article search, profile search | PRO-75 | 10074 | Task | Code review/test | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 18:57 | 2023-10-18 18:11 | 2023-10-04 15:53 |  |  | 0 | *Success Criteria:* Update the landing page and header pages as per specification of P4 wireframes. This includes the implementation of Saved pages - dependent on [https://deco3801.atlassian.net/browse/PRO-73¦https://deco3801.atlassian.net/browse/PRO-73¦smart-link] and [https://deco3801.atlassian.net/browse/PRO-72¦https://deco3801.atlassian.net/browse/PRO-72¦smart-link] The dropdown wireframes have not been created so you will have to be creative !image-20230920-085648.png¦width=729,height=292! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-73 | [18 empty] | 20/Sep/23 6:57 PM;6393c7579960988ef6c31a45;image-20230920-085648.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10020 | [25 empty] | P4 | 0¦i0003r:k |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 2 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | In Progress
UI implementation ¦ Saved Pages | PRO-74 | 10073 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 18:53 | 2023-10-18 18:10 | 2023-10-17 22:37 | 2023-10-18 18:10 |  | 0 | *Success Criteria:* Build button for save page search as per specification of wireframe below. Incorporate API as designed in PRO-73 !image-20230920-085246.png¦width=770,height=921! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-73 | [17 empty] | PRO-76 | 20/Sep/23 6:53 PM;6393c7579960988ef6c31a45;image-20230920-085246.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10019 | [26 empty] | 0¦i0003r:04 |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 3 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | Done
Backend ¦ Saved pages | PRO-73 | 10072 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 18:50 | 2023-10-02 10:02 | 2023-10-17 22:41 | 2023-10-02 10:02 |  | 0 | *Context:* Phase 4 features includes a ‘save pages’ feature, where a user can save an article they are looking at and access this in the main banner. *Success criteria:* Develop (potentially two) routes; to handle the saving of article into the SessionManager, and another to retrieve the headers of saved articles. *Suggestions:* * Update SessionManager for saved articles * create routes to handle save/retrieve |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-72 |  |  |  |  | PRO-74 | PRO-75 | [38 empty] | P4 | 0¦i0003s:l |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 5 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
Phase 4 API routes | PRO-72 | 10071 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-20 18:43 | 2023-09-24 17:05 | 2023-10-17 22:41 | 2023-09-24 17:05 |  | 0 | *Context:* The scope has increased, and more data will need to be managed between backend and UI for polling, commenting and politician updates. A number of jiras will be linked to this. For each of the jiras, determine whether a API endpoint will be required (or whether an existing endpoint will suffice). *Success Criteria:* Document all P4 API routes needed in the following file: [https://deco3801.atlassian.net/wiki/spaces/KB/pages/4194312/P4+-+API+Endpoints¦https://deco3801.atlassian.net/wiki/spaces/KB/pages/4194312/P4+-+API+Endpoints¦smart-link] |  | Daniel Ciccotosto-Camp | Darren Ooi | 6393c7579960988ef6c31a45 | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | [13 empty] | PRO-73 | PRO-68 | PRO-78 | PRO-80 | PRO-81 | PRO-82 | PRO-84 | PRO-86 | PRO-77 | PRO-87 | PRO-90 |  |  |  | 22/Sep/23 1:26 PM;6393c7579960988ef6c31a45;image-20230922-032432.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10029 | [25 empty] | P4 | 0¦i0003v: |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 5 |  |  |  |  | 1 |  | 45191.1547 | 22/Sep/23 1:26 PM;6393c7579960988ef6c31a45;I’m still finding some of the responses in the doc a little vague; for example, a list of headers for popular articles and recent articles. Would popular articles be an ordered list of article headers, and if so, the intention would be to link this back to the original page, so do you have enough data here to enable that? !image-20230922-032432.png¦width=765,height=205! | 22/Sep/23 1:42 PM;712020:ba48493f-ddfd-47bd-9785-e143eca6e14b;[~accountid:6393c7579960988ef6c31a45] we can have a discussion on whether the list will be ordered, I don't have a preference. Once I have the headers for the popular/recent articles the intention is to use /getArticle route to get all other information about the specific article once clicked on. I have worked with Ron to update some of the routes yesterday and will update the doc accordingly soon. | 10008 | Backend | Done
Repipe frontend to pass only url for backend queries | PRO-71 | 10070 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | 2023-09-20 16:11 | 2023-09-24 17:05 | 2023-10-19 22:03 | 2023-09-24 17:05 |  | 0 | [42 empty] | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | [16 empty] | 0¦i0003v:1 |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 | [8 empty] | 1 |  |  |  |  | 10002 | Frontend | Done
New features to be implemented | PRO-70 | 10069 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-17 16:50 | 2023-09-20 18:50 | 2023-09-17 16:51 | 2023-09-20 15:38 |  | 0 | *Success Criteria:* * Have discussion with each other regarding any new features to be implemented. * Pen to paper of new features, plus relevant wireframe * Discussion with [~accountid:6393c7579960988ef6c31a45] to create technical jiras for the rest of the team. +_Potential new features?_+ * commenting system ** tiktok accounts * toggle between dot point and paragraph form * adding campaigns and parties for political figures * copy to clipboard * open new tab - visit article |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Yash sharma | 60b36ba8a5be0a0069a85cd2 | [16 empty] | 0¦i00042:0u |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 5 |  |  |  |  | 1 |  |  |  |  | 10054 | designing | Done
API Implementation - political figure webpage | PRO-68 | 10067 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-17 16:00 | 2023-10-01 15:57 | 2023-10-01 15:51 | 2023-10-01 15:57 |  | 0 | *Success Criteria* * Configure and develop API calls to handle requests from the user interface. Organise conversation with UI leads [~accountid:712020:c2246c89-3dcf-455f-aa78-d1549598901c] or [~accountid:712020:ba48493f-ddfd-47bd-9785-e143eca6e14b] |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-65 | PRO-58 | PRO-59 | PRO-66 | PRO-72 | [23 empty] | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | [15 empty] | P3 | 0¦i0003s:k |  | DECO3801 Sprint 3 ¦ P4 |  |  |  |  | 2 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
Storyboarding and wireframe design - recent articles collection | PRO-67 | 10066 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-17 15:54 | 2023-09-20 15:38 | 2023-09-17 16:42 | 2023-09-20 15:38 |  | 0 | *Context* As we begin to develop more features specific to our target demographic, we have begun discussions to develop a political figure webpage. A subheading in this webpage will feature all the articles they will be featured in, but the wireframe design and user journey for this feature has not been fully elaborated. *Success criteria:* * develop a user journey regarding the recent article collection on a political figure webpage. Discuss and provide an updated wireframe design that would enhance the user’s experience of the application. Section shown for reference. !image-20230917-055410.png¦width=586,height=240! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 17/Sep/23 3:54 PM;6393c7579960988ef6c31a45;image-20230917-055410.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10018 | [26 empty] | 0¦i00042:0u6 |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 3 |  |  |  |  | 1 |  |  |  |  | 10054 | designing | Done
Session Manager | PRO-66 | 10065 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-10 16:57 | 2023-09-21 19:00 | 2023-10-01 10:40 | 2023-09-21 19:00 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-68 | [39 empty] | P3 | 0¦i0003x: |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 |  |  |  | 10 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
Create initial Database structures | PRO-65 | 10064 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-10 16:40 | 2023-09-17 16:00 | 2023-09-13 16:17 | 2023-09-15 10:43 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-57 | PRO-68 | [38 empty] | P3 | 0¦i00042:0u4 |  | DECO3801 Sprint 3 ¦ P2 | [9 empty] | 0 |  |  | 13/Sep/23 4:17 PM;6393c7579960988ef6c31a45;{noformat}DROP TABLE IF EXISTS Article DROP TABLE IF EXISTS Politician DROP TABLE IF EXISTS Politician_Position DROP TABLE IF EXISTS Politician_PositionNameCodes DROP TABLE IF EXISTS Politician_NameCodes DROP TABLE IF EXISTS Politician_KeyTable CREATE TABLE Politician_PositionNameCodes ( ID INT AUTO_INCREMENT PRIMARY KEY, NameCode VARCHAR(255) NOT NULL UNIQUE, InProduction BOOLEAN, InsertedAt DATETIME, InsertedBy VARCHAR(50) ); CREATE TABLE Article ( ID INT AUTO_INCREMENT PRIMARY KEY, URL VARCHAR(255), -- Adjust the length as needed for your URLs UpperBias DECIMAL(5, 2), -- 5 total digits with 2 decimal places LowerBias DECIMAL(5, 2), -- lower bias score Summary TEXT, -- TEXT type allows up to 65,535 characters InProduction BOOLEAN, InsertedAt DATETIME, InsertedBy VARCHAR(50) ); CREATE TABLE Politician ( ID INT AUTO_INCREMENT PRIMARY KEY, Fname VARCHAR(255), Lname VARCHAR(255), About VARCHAR(1500), Age INT, Gender VARCHAR(255), InProduction BOOLEAN, InsertedAt DATETIME, InsertedBy VARCHAR(50) ); CREATE TABLE Politician_Position ( ID INT AUTO_INCREMENT PRIMARY KEY, PositionNameCode VARCHAR(255), InProduction BOOLEAN, InsertedAt DATETIME, InsertedBy VARCHAR(50), FOREIGN KEY (PositionNameCode) REFERENCES Politician_PositionNameCodes(NameCode) ); CREATE TABLE Politician_KeyTable ( ID INT AUTO_INCREMENT PRIMARY KEY, ID_Politician INT, ID_Article INT, InProduction BOOLEAN, InsertedAt DATETIME, InsertedBy VARCHAR(50), FOREIGN KEY (ID_Politician) REFERENCES Politician(ID), FOREIGN KEY (ID_Article) REFERENCES Article(ID) );{noformat} |  | 10008 | Backend | Done
Investigation ¦ table structures | PRO-63 | 10062 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-10 15:57 | 2023-09-13 10:47 | 2023-10-19 22:03 | 2023-09-13 10:47 |  | 0 | Develop an exhaustive list of table structures that will need to be implemented for our NewsCuration website !image-20230910-231259.png¦width=690,height=526! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 11/Sep/23 9:13 AM;70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a;image-20230910-231259.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10017 | [25 empty] | P3 | 0¦i00042:0ui |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 4 |  |  |  |  | 0 |  |  |  |  | 10054 | designing | Done
implementation ¦ establish remote database connection and transaction client | PRO-62 | 10061 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-10 10:16 | 2023-09-17 15:54 | 2023-10-19 22:03 | 2023-09-15 10:21 |  | 0 | *Context:* We need to persist the article, politician and other related data so all developers can operate on a single copy of data. We also need to keep versioning of the data, and logs to maintain the status and operations of the database. *Success criteria:* * Develop a cloud solution that operates with an AWS RDS server, transacts new records and facilitates query operations |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i00042:0u9 |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 10 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
UI implementation ¦ bias breakdown touch-ups | PRO-61 | 10060 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 16:58 | 2023-10-04 15:51 | 2023-10-04 15:51 |  |  | 0 | *Success criteria:* * This Jira is used as a placeholder to complete the bias article breakdown webpage to the specification of the wireframe design. Carefully look at the wireframe in image 6 and incorporate any features that have been omitted from the prior jiras. * Before beginning work, make sure that you have pulled the most up to date version of the webpage * Meet with a BA for testing for signoff, before a merge request is actioned. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 08/Sep/23 4:58 PM;6393c7579960988ef6c31a45;image-20230908-065837.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10016 | [20 empty] | Impediment |  |  |  |  | P4 | 0¦i000bb: | [6 empty] | 3 |  |  |  |  | 2 |  |  | 04/Oct/23 3:51 PM;6393c7579960988ef6c31a45;(flag) Flag added delete |  | 10002 | Frontend | To Do
User experience development ¦ politician webpage | PRO-59 | 10058 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 16:51 | 2023-09-24 17:05 | 2023-09-24 16:32 | 2023-09-24 17:05 |  | 0 | *Success Criteria:* * Develop the webpage as per the specifications of the wireframe design listed below. NOTE: this Jira requires the user interface components only, and not implementation of API calls to retrieve ‘recent articles' ‘filtered summary’, ‘about’ or a profile picture and country flag. This will be completed in future implementation. All sections that require an API endpoint should be styled, but not present during this build * Test with a BA to make sure the website meets the wireframe specifications !image-20230908-063719.png¦width=994,height=923! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-68 | [13 empty] | 08/Sep/23 4:51 PM;6393c7579960988ef6c31a45;image-20230908-063719.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10014 | [26 empty] | 0¦i0003v:0i |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 | [8 empty] | 3 |  |  | 13/Sep/23 4:16 PM;6393c7579960988ef6c31a45;in pseudocode, write all the API endpoint fns you will require in backend e.g. inp (politician name) → out(all politician info) |  | 10002 | Frontend | Done
Implementation ¦ construct query handlers for RDS | PRO-58 | 10057 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 16:32 | 2023-09-17 16:00 | 2023-09-10 16:56 | 2023-09-15 10:43 |  | 0 | *Context:* Our project will the storage of a large amount of data into the RDS to handle the politicians, articles and article bias, summaries and keywords from the text. *Success criteria:* * Create an exhaustive list of wrapper functions that will enable us to insert new values into the AWS RDS system. Make sure to document the tables properly, and include a well-documented header to each page |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-68 | [39 empty] | P3 | 0¦i00042:0u2 |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 10 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
Implementation ¦ persons of interest in article | PRO-57 | 10056 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 16:27 | 2023-09-17 16:42 | 2023-09-17 16:42 | 2023-09-17 16:42 |  | 0 | *UC:* WHEN I read in an article THEN a list of names should be extracted from the list, and the list of names should be persisted to the database. *Success criteria:* Develop a script/function that will allow for us to extract user names and profiles from an article and persist this to a database. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-65 |  |  |  |  | PRO-56 | [40 empty] | 0¦i00042:0ud |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 3 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
UI implementation ¦ Persons of interest | PRO-56 | 10055 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 16:17 | 2023-10-15 17:22 | 2023-10-15 17:18 | 2023-10-15 17:22 |  | 0 | *Success Criteria:* * *Develop the UI component* and *implement* the persons of interest as per the specifications of a wireframe design. Coordinate the API call with the developer of PRO-xx regarding the implementation of user search !image-20230908-061654.png¦width=937,height=325! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-57 | PRO-80 | [17 empty] | 08/Sep/23 4:17 PM;6393c7579960988ef6c31a45;image-20230908-061654.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10013 | [26 empty] | 0¦i0003r:c |  | DECO3801 Sprint 3 ¦ P4.2 |  |  |  |  | 3 |  |  |  |  | 0 |  |  |  |  | 10002 | Frontend | Done
designing | PRO-55 | 10054 | Epic | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:53 | 2023-09-08 15:53 | 2023-10-19 22:03 |  |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [35 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [14 empty] | dark_green |  |  |  | 0¦i0009z: | [18 empty] | To Do
Wireframe design ¦ political figure browsing | PRO-54 | 10053 | Task | Code review/test | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Yash sharma | 60b36ba8a5be0a0069a85cd2 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:53 | 2023-10-04 15:04 | 2023-09-17 15:49 |  |  | 0 | *Success criteria:* * Build a wireframe to outline the webpage that will enable users to search and filter for political figures. This will form the basis of our Phase IV. * Start conversation with Daniel and Yash before adding to group discussion |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i0003s: |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  |  | 0 |  |  |  |  | 3 |  |  |  |  | 10054 | designing | In Progress
UI development and implementation ¦ TTS | PRO-53 | 10052 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:52 | 2023-09-24 17:01 | 2023-10-19 22:03 |  |  | 0 | *Success criteria:* From research undertaken in [https://deco3801.atlassian.net/browse/PRO-52¦https://deco3801.atlassian.net/browse/PRO-52¦smart-link] , *develop* and *implement* the text to speech buttons as per the specifications of the wireframe designs below: NOTEL the icon for TTS should be updated to reflect the sound icon, i.e. the icon should appear as[ 🔊 ] not [ 🎤 ] !image-20230908-055059.png¦width=992,height=545! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-52 | [18 empty] | 08/Sep/23 3:52 PM;6393c7579960988ef6c31a45;image-20230908-055059.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10012 | [20 empty] | Impediment | [5 empty] | 0¦i0009j: | [6 empty] | 3 |  |  |  |  | 1 |  |  | 24/Sep/23 5:01 PM;6393c7579960988ef6c31a45;(flag) Flag added delete |  | 10002 | Frontend | To Do
research and development ¦ TTS | PRO-52 | 10051 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:47 | 2023-09-24 17:01 | 2023-09-24 17:06 |  |  | 0 | Text-To-Speech (TTS) is one of the accessibility features we intend to implement into the article search page *Success criteria:* * research the viability of text to speech and determine whether additional controls in the backend are needed. If the time consumed to organise TTS is tedious, reconvene at next meeting to consider removing it from scope. From a little bit of researching [https://www.hongkiat.com/blog/text-to-speech/¦https://www.hongkiat.com/blog/text-to-speech/¦smart-link] |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-53 | [34 empty] | Impediment | [5 empty] | 0¦i0009b: | [6 empty] | 3 |  |  |  |  | 0 |  |  | 24/Sep/23 5:01 PM;6393c7579960988ef6c31a45;(flag) Flag added delete |  | 10008 | Backend | To Do
User experience & implementation ¦ text size | PRO-51 | 10050 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:41 | 2023-10-10 15:29 | 2023-10-15 17:10 | 2023-10-10 15:29 |  | 0 | *Success criteria* * Construct a slider component and implementation that will allow for text underneath to vary in size, depending on the range of the slider. The effect should be signed off by the Business Analysis before pull request is completed. !image-20230908-054101.png¦width=1134,height=667! |  | Daniel Ciccotosto-Camp | Manav Trivedi | 6393c7579960988ef6c31a45 | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | [27 empty] | 08/Sep/23 3:41 PM;6393c7579960988ef6c31a45;image-20230908-054101.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10011 | [26 empty] | 0¦i0003r:3 |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  |  | 3 |  |  |  |  | 0 |  | 45209.2289 | 10/Oct/23 3:29 PM;712020:c2246c89-3dcf-455f-aa78-d1549598901c;Not worth doing the functionality, added a visual placeholder instead |  | 10002 | Frontend | Done
User experience ¦ vertical lettering | PRO-50 | 10049 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:35 | 2023-09-24 17:03 | 2023-10-19 22:03 | 2023-09-24 17:03 |  | 0 | *Success criteria:* * develop a component that stretches the lengths of the panels of the wireframe, as outlined in the image below * This should be a reusable component for subsequent sections |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 08/Sep/23 3:35 PM;6393c7579960988ef6c31a45;image-20230908-053523.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10010 | [26 empty] | 0¦i0003v:2 |  | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 |  |  |  | 3 |  |  |  |  | 0 |  |  |  |  | 10002 | Frontend | Done
User experience ¦ tabs | PRO-49 | 10048 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:33 | 2023-09-17 16:48 | 2023-09-17 16:48 | 2023-09-17 16:48 |  | 0 | *Success criteria:* * Build tabs as per the specifications of the wireframes, EXCEPT that the tabs should be positioned on the right right corner of the page, instead of the top left corner of the page. !image-20230908-053139.png¦width=1230,height=436! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 08/Sep/23 3:33 PM;6393c7579960988ef6c31a45;image-20230908-053139.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10009 | [25 empty] | P2 | 0¦i00042:0ti |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 3 |  |  |  |  | 0 |  |  | 17/Sep/23 4:48 PM;6393c7579960988ef6c31a45;OOS: no longer required |  | 10002 | Frontend | Done
Storyboarding - capture user experiences and needs | PRO-48 | 10047 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Yash sharma | 60b36ba8a5be0a0069a85cd2 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-08 15:28 | 2023-09-20 15:38 | 2023-10-19 22:03 | 2023-09-20 15:38 |  | 0 | The tutor feedback has asked for more specific edge cases of our project - how would our user profiles interact with our current project, and which additional features could discretely impact and improve the user’s experience? *Success Criteria:* Construct storyboards our intended target audience’s use of the app and discuss insights at our next group meeting |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | [16 empty] | 0¦i00042:0tr |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 10 |  |  |  |  | 0 |  |  |  |  | 10004 | Reporting | Done
Bias prompt | PRO-47 | 10046 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-09-06 22:22 | 2023-09-08 08:45 | 2023-10-06 14:20 | 2023-09-08 08:45 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i00042:4 |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
Pipe chatGPT to word scraper | PRO-46 | 10045 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | 2023-08-23 14:22 | 2023-08-23 16:45 | 2023-10-19 22:03 | 2023-08-23 16:45 |  | 0 | [60 empty] | 0¦i00046: |  | DECO3801 Sprint 3 ¦ P1 | [9 empty] | 1 | [6 empty] | Done
UI implementation ¦ bias keywords | PRO-44 | 10043 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-20 12:52 | 2023-09-10 16:44 | 2023-10-19 22:03 | 2023-09-10 16:44 |  | 0 | *Success Criteria:* * Using the Implementation from [https://deco3801.atlassian.net/browse/PRO-26¦https://deco3801.atlassian.net/browse/PRO-26¦smart-link] , develop the UI as per specification of the wireframe !image-20230820-025215.png¦width=534,height=598! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [28 empty] | 20/Aug/23 12:52 PM;6393c7579960988ef6c31a45;image-20230820-025215 (c39e0b84-1f26-4e3e-b75a-b6d0fee77904).png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10006 | 20/Aug/23 12:52 PM;6393c7579960988ef6c31a45;image-20230820-025215.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10005 | [24 empty] | P2 | 0¦i00042:0v |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 10 |  |  |  |  | 2 |  |  |  |  | 10002 | Frontend | Done
UI Implementation ¦ summarise article | PRO-43 | 10042 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-20 12:45 | 2023-09-03 17:41 | 2023-10-19 22:03 | 2023-09-03 17:41 |  | 0 | *Success criteria:* with the implementation completed in [https://deco3801.atlassian.net/browse/PRO-42¦https://deco3801.atlassian.net/browse/PRO-42¦smart-link], adopt the prompt into the UI as per specifications of the wireframe below. !image-20230820-024622.png¦width=538,height=542! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-29 | PRO-42 | [17 empty] | 20/Aug/23 12:46 PM;6393c7579960988ef6c31a45;image-20230820-024622.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10003 | [26 empty] | 0¦i00045:i |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 5 |  |  |  |  | 1 |  |  |  |  | 10002 | Frontend | Done
Implementation ¦ summarise article | PRO-42 | 10041 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-20 12:40 | 2023-09-08 08:44 | 2023-10-19 22:03 | 2023-09-08 08:44 |  | 0 | *Success Criteria:* thoughtfully develop a Chatgpt prompt to summarise a text, to exclude emotionally charged language and bias. Carefully test the prompt on a variety of examples. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-43 | [39 empty] | P1 | 0¦i00042:i |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 4 |  |  |  |  | 2 |  |  |  |  | 10008 | Backend | Done
Implementation ¦ web scraper | PRO-39 | 10038 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-20 12:32 | 2023-08-23 16:45 | 2023-10-19 22:03 | 2023-08-23 16:45 |  | 0 | *Success Criteria:* * Successfully web scrape a media article as input to the large language model. This does not include UI implementation. Given URL, needs to output: ** Title of the article ** All paragraphs in the articles as a single paragraph |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P2 | 0¦i00046:i |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 4 |  |  |  |  | 2 |  |  |  |  | 10008 | Backend | Done
EOP2 ¦ Admin/Documentation check | PRO-37 | 10036 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 09:52 | 2023-08-18 09:55 | 2023-10-19 22:03 |  |  | 0 | *Success Criteria:* * Ensure there is no missing documentation in anticipation for Assessment item 3 This should be performed before the end of Phase 1 |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P2 | 0¦i0006v: | [6 empty] | 5 |  |  |  |  | 0 |  |  |  |  | 10003 | Admin | To Do
EOP1 ¦ Admin/Documentation check | PRO-36 | 10035 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 09:52 | 2023-09-21 21:40 | 2023-09-21 21:40 | 2023-09-21 21:40 |  | 0 | *Success Criteria:* * Ensure there is no missing documentation in anticipation for Assessment item 3 This should be performed before the end of Phase 1 |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i0003w: |  | DECO3801 Sprint 3 ¦ P1 | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 |  |  | 5 |  |  |  |  | 0 |  |  |  |  | 10003 | Admin | Done
UI implementation ¦ Bias score | PRO-34 | 10033 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 09:46 | 2023-09-08 08:44 | 2023-10-19 22:03 | 2023-09-08 08:44 |  | 0 | *Success Criteria:* # Implement bias score as per the UI specification !image-20230820-024904.png¦width=535,height=596! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-28 | [18 empty] | 20/Aug/23 12:49 PM;6393c7579960988ef6c31a45;image-20230820-024904.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10004 | [25 empty] | P1 | 0¦i00043:i |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 3 |  |  |  |  | 2 |  |  |  |  | 10002 | Frontend | Done
OOS: Implementation ¦ Retrieval of similar news articles | PRO-33 | 10032 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 09:37 | 2023-09-10 12:43 | 2023-10-19 22:03 | 2023-09-10 12:43 |  | 0 | *Success Criteria:* * Develop an algorithm to find related news articles to inputted text as per the specification in PRO-31 |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P3 | 0¦i00042:1 |  | DECO3801 Sprint 3 ¦ P2 |  |  |  |  | 5 |  |  |  |  | 3 |  |  |  |  | 10008 | Backend | Done
OOS: Requirements gathering ¦ retrieval of similar web articles | PRO-32 | 10031 | Task | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 09:35 | 2023-09-08 15:20 | 2023-10-19 22:03 |  |  | 0 | *Context:* In phase 3 of our build, we intend to scrape together alternative websites relating to the same news content to generate comparative bias scores. This will likely require some investigation into Search Engine Optimisation (SEO) techniques over multiple search criteria. *Success Criteria:* # Create a confluence page documenting a process for finding articles relating to the same topic. Note this is a requirements gathering Jira - the implementation will be related to a separate jira. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P3 | 0¦i0005r: | [6 empty] | 10 |  |  |  |  | 2 |  |  |  |  | 10008 | Backend | To Do
UI development ¦ P1 | PRO-29 | 10028 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 08:55 | 2023-09-01 18:43 | 2023-10-19 22:03 | 2023-09-01 18:43 |  | 0 | *Context:* Develop the user interface with React/next.js for Phase 1 of the project, as per specification of [https://deco3801.atlassian.net/browse/PRO-24¦https://deco3801.atlassian.net/browse/PRO-24¦smart-link] *Success Criteria:* Create the following UI according to the image below. !image-20230820-022446.png¦width=1068,height=687! |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-24 |  |  |  |  | PRO-43 | [13 empty] | 20/Aug/23 12:25 PM;6393c7579960988ef6c31a45;image-20230820-022446.png;https://deco3801.atlassian.net/rest/api/3/attachment/content/10000 | [26 empty] | 0¦i00044: |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 5 |  |  |  |  | 2 |  |  |  |  | 10002 | Frontend | Done
Implementation ¦ Bias/trust indicator | PRO-28 | 10027 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 08:33 | 2023-09-08 08:45 | 2023-10-19 22:03 | 2023-09-08 08:45 |  | 0 | *Context:* In Phase 2, we intend to develop a bias score to provide users with a trust indicator of the news sources which are inputted into the webpage. After the scope of work bias score is properly planned, requirements for the technical implementation (and the existing technologies to achieve this) will need to be investigated. This Jira is dependent on [https://deco3801.atlassian.net/browse/PRO-21¦https://deco3801.atlassian.net/browse/PRO-21¦smart-link] |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [9 empty] | PRO-21 |  |  |  |  | PRO-34 | [39 empty] | P1 | 0¦i00042:9 |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 8 |  |  |  |  | 3 |  |  |  |  | 10008 | Backend | Done
Presentation Task | PRO-27 | 10026 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Yash sharma | 60b36ba8a5be0a0069a85cd2 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-18 08:26 | 2023-08-30 12:00 | 2023-10-19 22:03 | 2023-08-30 11:59 |  | 0 | *Context:* The presentation task is the second assessment item for this subject, and is worth 20% of our overall grade. It requires a powerpoint presentation to be submitted for a presentation in week 6. This Jira is a placeholder - it can be deleted, flagged or further elaborated closer to the due date UI wireframes should be drawn prior to this assessment item |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i00045: |  | DECO3801 Sprint 3 ¦ P1 | [9 empty] | 0 |  |  | 20/Aug/23 1:23 PM;6393c7579960988ef6c31a45;Conversations with UI - [~accountid:712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162] Conversations with Phases - [~accountid:6393c7579960988ef6c31a45] Technical - [~accountid:712020:ba48493f-ddfd-47bd-9785-e143eca6e14b] |  | 10004 | Reporting | Done
TESTING ¦ bias keywords & summary text | PRO-26 | 10025 | Task | In Progress | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-17 22:32 | 2023-10-04 15:04 | 2023-09-10 17:14 |  |  | 0 | *Context:* Phase 1 of our build adopts an existing LLM to give the reader context about a potentially biased news article. Although the API works in python, testing with multiple news articles to test the robustness of the output still needs to occur *Success Criteria:* # As a group, decide on an acceptable summary text to provide to the reader # Test the robustness of the prompt with several examples, ranging from editorials to formal enquiries |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P1 | 0¦i00040: |  | DECO3801 Sprint 3 ¦ P1 | DECO3801 Sprint 3 ¦ P2 | DECO3801 Sprint 3 ¦ P4 | DECO3801 Sprint 3 ¦ P4.2 |  | 0 |  |  |  |  | 10 |  |  | 22/Aug/23 1:01 PM;6393c7579960988ef6c31a45;Keeping this here as a placeholder for code review |  | 10003 | Admin | In Progress
PLACEHOLDER ¦ wireframes for UI P1 | PRO-24 | 10023 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-17 20:06 | 2023-09-08 08:49 | 2023-10-19 22:03 | 2023-09-08 08:49 |  | 0 | *Success Criteria:* * Create high-fidelity wireframes of the newsCuration application P1 phase * A confluence page with all the details added. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-29 | [39 empty] | P1 | 0¦i00042:2 |  | DECO3801 Sprint 3 ¦ P1 |  |  |  |  | 2 |  |  |  |  | 0 |  |  | 20/Aug/23 12:50 PM;6393c7579960988ef6c31a45;See [https://deco3801.atlassian.net/wiki/spaces/KB/pages/2031617/Wireframes¦https://deco3801.atlassian.net/wiki/spaces/KB/pages/2031617/Wireframes¦smart-link] |  | 10002 | Frontend | Done
Send python GPT response to next.js | PRO-23 | 10022 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-13 22:07 | 2023-08-15 08:12 | 2023-10-19 22:03 | 2023-08-15 08:12 |  | 0 | Success criteria is defined as above. Inform all other developers [~accountid:6393c7579960988ef6c31a45] [~accountid:712020:c2246c89-3dcf-455f-aa78-d1549598901c] [~accountid:70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a] when this is completed. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | [16 empty] | 0¦i0003r: |  | DECO3801 Sprint 2 |  |  |  |  | 3 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
Bias score research | PRO-21 | 10020 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-13 21:58 | 2023-08-20 13:18 | 2023-10-19 22:03 | 2023-08-20 13:18 |  | 0 | *Context*: we intend to implement a ‘bias score’ which will rate the amount of emotionally charge text, and bias in text. The implementation of this may not be so straightforward; and the response from an LLM such as chat GPT may not be sufficient to build a rating. In addition to this, the rating of ‘bias’ in text is not so straightforward; bias can manifest in political leanings, or with emotional subtext to incentivize payment. *Success criteria* * Create a confluence page that outlines the types of bias in text. This is research based only - no implementation is required |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [14 empty] | PRO-28 | [22 empty] | Yash sharma | 60b36ba8a5be0a0069a85cd2 | [16 empty] | 0¦i00034: |  | DECO3801 Sprint 2 |  |  |  |  | 10 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
Testing chat GPT prompts | PRO-20 | 10019 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-13 18:43 | 2023-08-20 13:18 | 2023-10-19 22:03 | 2023-08-20 13:18 |  | 0 | * Testing chat GPT 3.5 turbo prompt to summarise biased/charged language |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦i00033: |  | DECO3801 Sprint 2 |  |  |  |  | 5 |  |  |  |  | 0 |  |  |  |  | 10008 | Backend | Done
Statement of work - Yash Section | PRO-19 | 10018 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Yash sharma | 60b36ba8a5be0a0069a85cd2 | Yash sharma | 60b36ba8a5be0a0069a85cd2 | Yash sharma | 60b36ba8a5be0a0069a85cd2 | 2023-08-13 18:39 | 2023-08-20 13:18 | 2023-10-19 22:03 | 2023-08-20 13:18 |  | 0 | * outline * f * g | [41 empty] | Yash sharma | 60b36ba8a5be0a0069a85cd2 | [16 empty] | 0¦i00033:i |  | DECO3801 Sprint 2 | [9 empty] | -2 |  |  |  |  | 10004 | Reporting | Done
SOW: Project deliverables, Your teams assumptions | PRO-18 | 10017 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | Ron Ashri | 70121:6ffa6589-34c6-4180-b13a-22c0c59a6e1a | 2023-08-13 18:26 | 2023-08-15 13:52 | 2023-10-19 22:03 | 2023-08-15 13:52 |  | 0 | flesh out dot points of Project deliverables, Your teams assumptions. | [59 empty] | 0¦i0003j: |  | DECO3801 Sprint 2 | [9 empty] | 1 |  |  |  |  | 10004 | Reporting | Done
Test chat GPT API | PRO-17 | 10016 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-12 17:39 | 2023-08-13 18:42 | 2023-10-19 22:03 | 2023-08-12 20:59 |  | 0 | Print a chapt GPT response to screen |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | [16 empty] | 0¦hzzzzb: |  | DECO3801 Sprint 0 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 10008 | Backend | Done
UI mockups/finalisation | PRO-15 | 10014 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:52 | 2023-08-20 13:18 | 2023-10-19 22:03 | 2023-08-20 13:18 |  | 0 | *Context:* We intend to create a desktop application that when prompted with a news article or related paraphernalia, will be able to distinguish/observe the bias in the text. *Acceptance criteria:* * Create wireframes in Adobe XD that is exhaustive of all the features we intend to implement into our desktop we application. Features should be verified with user testing, at the discretion of the assignee of this issue. * The features evident in prototyping must align with the Statement of Work (SOW) due 18th August. Conversations between the author of the SOW and wireframes must occur to ensure consistency between both elements. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [54 empty] | P1 | 0¦i00033:9 |  | DECO3801 Sprint 0 | DECO3801 Sprint 2 |  |  |  | 10 |  |  |  |  | 8 |  |  |  |  | 10002 | Frontend | Done
Confluence Documents for setup | PRO-14 | 10013 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:46 | 2023-08-16 19:53 | 2023-10-19 22:03 | 2023-08-16 19:53 |  | 0 | *Acceptance criteria:* * Create a confluence location, that will store all issues and setup relating to development setup, issues and workarounds. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Sean DM | 712020:a17e2b89-9ef8-4ddd-bd82-3582d2624162 | [16 empty] | 0¦i00037: |  | DECO3801 Sprint 0 | DECO3801 Sprint 2 | [8 empty] | 0 |  |  | 12/Aug/23 2:01 PM;6393c7579960988ef6c31a45;Confluence page with chat-gpt API and documentation can be found [here¦https://deco3801.atlassian.net/wiki/spaces/KB/pages/983041/Chat+GPT+API+key+and+info+details] |  | 10003 | Admin | Done
Build codebase and relevant documentation | PRO-13 | 10012 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:44 | 2023-08-16 19:53 | 2023-10-19 22:03 | 2023-08-16 19:53 |  | 0 | *Acceptance criteria:* * Build a new repository on Github and invite all team members, including BA’s |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [16 empty] | 0¦i00035: |  | DECO3801 Sprint 0 | DECO3801 Sprint 2 |  |  |  | 1 |  |  |  |  | 0 |  |  | 13/Aug/23 10:10 PM;6393c7579960988ef6c31a45;I’m going to leave this here but assign it to me. I want everyone to have no issues spinning up the web application locally |  | 10003 | Admin | Done
Create chat GPT API account and load with funds | PRO-12 | 10011 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:42 | 2023-08-12 14:03 | 2023-10-06 14:20 | 2023-08-12 14:03 |  | 0 | *Context:* We are beginning to setup a web application with API integration for chatGPT. This requires an account setup, loaded with funds so that a token is generated that will faciliate chat GPT requests. *Acceptance Criteria:* * Create a confluence page, outlining the account details and funds loaded into the account. * Test an API request within python only. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Yash sharma | 60b36ba8a5be0a0069a85cd2 | [16 empty] | 0¦hzzzzj: |  | DECO3801 Sprint 0 |  |  |  |  | 5 |  |  |  |  | 2 |  |  | 12/Aug/23 2:02 PM;6393c7579960988ef6c31a45;Relevant documentation can be found [here¦https://deco3801.atlassian.net/wiki/spaces/KB/pages/983041/Chat+GPT+API+key+and+info+details] |  | 10003 | Admin | Done
Send button for prompt | PRO-11 | 10010 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:37 | 2023-08-12 21:00 | 2023-10-19 22:03 | 2023-08-12 21:00 |  | 0 | *Context:* We are beginning to create a user interface to handle chatGPT prompts before it is sent via HTTP request via flask to python. We need a button in our user interface that will begin this request. *Acceptance criteria*: * Create a ‘send’ button in user interface * Setup prompt request for CSI on react/next.js via Flask. This will also entail that the HTTP request is resolved in python |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [16 empty] | 0¦hzzzz3: |  | DECO3801 Sprint 0 | [9 empty] | 8 |  |  | 12/Aug/23 9:00 PM;6393c7579960988ef6c31a45;Test confirmed |  | 10002 | Frontend | Done
Input text field and gateway for GPT API | PRO-10 | 10009 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Manav Trivedi | 712020:c2246c89-3dcf-455f-aa78-d1549598901c | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:29 | 2023-08-13 12:57 | 2023-10-19 22:03 | 2023-08-13 12:57 |  | 0 | *Context:* We are beginning to build the UI that will serve as input for our chat GPT API. We will need to create a blank html (or similar page) that will capture the prompt before it is send via the GPT API. *Acceptance criteria:* WHEN I input a prompt into an input text field, on a html doc THEN the data is captured and stored such that it can be sent via API channels later on. |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [37 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [16 empty] | 0¦hzzzyv: |  | DECO3801 Sprint 0 |  |  |  |  | 5 |  |  |  |  | 3 |  |  |  |  | 10002 | Frontend | Done
Backend | PRO-9 | 10008 | Epic | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-10 08:23 | 2023-08-10 08:23 | 2023-10-19 22:03 |  |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [35 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [14 empty] | dark_orange |  |  |  | 0¦i00013: | [18 empty] | To Do
Reporting | PRO-5 | 10004 | Epic | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-09 17:22 | 2023-08-09 17:22 | 2023-10-19 22:03 |  |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [35 empty] | Yash sharma | 60b36ba8a5be0a0069a85cd2 | [14 empty] | dark_grey |  |  |  | 0¦i0000v: | [18 empty] | To Do
Admin | PRO-4 | 10003 | Epic | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  |  |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-09 17:22 | 2023-08-09 17:22 | 2023-10-19 22:03 |  |  | 0 | Administration |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [35 empty] | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | [14 empty] | yellow |  |  |  | 0¦i0000n: | [18 empty] | To Do
Frontend | PRO-3 | 10002 | Epic | To Do | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium |  | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-08-09 17:21 | 2023-10-15 21:30 | 2023-10-15 21:30 |  |  | 0 | All work relating to the user interface of this project |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [35 empty] | Darren Ooi | 712020:ba48493f-ddfd-47bd-9785-e143eca6e14b | [9 empty] | ghx-label-10 |  |  |  |  | blue |  |  |  | 0¦i0000f: | [18 empty] | To Do
Test Jira is working properly, | PRO-1 | 10000 | Task | Done | PRO | DECO3801 project | software | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 |  | Medium | Done | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | Daniel Ciccotosto-Camp | 6393c7579960988ef6c31a45 | 2023-07-28 09:05 | 2023-08-10 08:52 | 2023-10-19 22:03 | 2023-08-09 17:17 |  | 0 |  |  | Daniel Ciccotosto-Camp |  | 6393c7579960988ef6c31a45 | [55 empty] | 0¦hzzzzz: |  | DECO3801 Sprint 0 |  |  |  |  | 2 |  |  |  |  | 0 |  |  |  |  | 10003 | Admin | Done